## Risks and Contingency Plan
Distribution Chain | Risk | Description | Impact (out of 100) | Probability (%) | Preventive Actions | Contingency Plan | Restoration After Emergency State
Production | All electronic components to produce the device are running late, have been lost or stolen [p.1] | Given that the supplier has any type of complication, or the pieces have been stolen, etc. It wouldn't be possible to assemble Ec⌀. | 100 | 20 | Stock extra parts on a storehouse. Have different suppliers for every part in case one of them fails. Change the supplier if the problem persists. | Use the stockage in the stockhouse. In case there is not stock left, make a new order to the other supplier. | Stock extra parts. If the problem has happend more than 2 times, without a compelling reason, a new supplier should be found to provide the stockage.
| Broken machine in assembly line [p.2] | Due to a bad maintenance or by chance, one or more machines in the assembly line are broken. Not allowing the assembly of the device. | 100 | 9 | Perform periodical maintenance on the equipment and the machinery. | If it is a fast solucion: wait until the assembly line gets repaired. If it would take too long, go manual until the assembly line gets restored. | Make an investigation on what went wrong, an find a solution: maintenance more often, longer breaks, etc.
| Maintenance in assembly line [p.3] | To ensure proper operation in the assembly line, every piece of equipment and machinera goes through a periodical maintenance review. | 10 | 100 | Make the maintenance of the equipment when the production is at its lowest performance, or while the assembly line is not on production. | It the maintenance has to take place at the highest production peak, only the machinery is reviewed. In case it is the equipment the one needing the maintenance, it should be taken bit by bit. | Maintenance should be scheduled better next review to avoid affecting the production.
Development | Developers asking for sick leave [d.1] | Might occur that a developer(a) does not attend to his obligation due to sickness, personal issues or other compelling reasons. | 50 | 12 | Appropiate room temperatues, air flow, room luminosity, make good use of time so that the stressful delivery periods are shorthen, etc. Take the workplace risk prevention. | If the sick leave is for a long period of time, it might be advisable to find for a substitute. | Stand-up meeting to update the employee on the state of the project (changes during absence).
| Developer resigns [d.2] | Many are the reasons that could make a developer in the project resign from his position. This would leave the team without one or more members, therefore delaying the deadline. | 60 | 10 | Give the employees the most comfortable working-ambient: breaks, commodities, etc. | After the resignation has been posted, the negotations between company and employee take place. If the employee is not interested in continuing his work at the company, or the company decides the employee is not worth retaining: a selection process may start. If it is consired necessary, the selection process may start before knowing the outcome of the resignation. | The causes for the initial resignation must be looked for.
| Web page implementation delay [d.3] | During the web page design some problems occur and it is not possible to finish it in the due date. | 70 | 33 | Create a realistic set of project objectives and deliverable items within the provided timeframe. | Reduce unnecessary functionalities to make it to the due date. Simplify the front-end side and leave room for improvements after due date. | Start completing the functionalities that were postponed in previous phases of the development. Correct the simplified features in the front end implementation.
| Alexa implementation delay [d.4] | The implementation for the controlling and monitoring system included in Alexa cannot be completed in due time. | 65 | 40 | Create a realistic set of project objectives and deliverable items within the provided timeframe. | Focus the development of the webpage so that the device can be controlled with at least one of the user interfaces. | Continue the implementation of the Alexa Skill from where it was interrupted.
| Web page and Alexa implementation delay [d.5] | Both the Alexa service and the web page cannot be finished in the due date. | 95 | 14 | Create a realistic set of project objectives and deliverable items within the provided timeframe. | Postpone the deadline and focus resources in the web page main functionalities and aspect. | Correct the minor problems that might have been neglected before the due date (for the web page). The Alexa Skill development may continue where it was left off.
Security | Unauthorized access to the hardware [s.1] | The device can be manipulated by an user or an attacker wanting to know the innards of the device or with malicious intentions. | 80 | 5 | After all the testing and demonstrations are done, before the device is commercialized, protect the device from any user interaction. | If it is known that the device has been manipulated in any way by an unauthorized user, the company can reserve the right to take legal actions against the perpetrator. | After the unauthorized manipulation, the company will not take responsability of any reparation.
| Unauthorized access to the web page/Alexa [s.2] | Attackers might find a way of spoofing the identity of the user and perform undesired interactions with the service. | 100 | 48 | Use JWT (JSON Web Token - token encoded from data payload using a secret established the server) to authenticate the user and share the information with the server. | Lock any non-automated action until the user resets all credentials and performs the security checks requested by the Rainforest Security Team. User must be notified of the security breach. | The service should be unlocked an notified to the user. The implementation of further security measures should be taken into account.
| Unauthorized access to the infrastructure of the company [s.3] | The servers or headquarters might suffer a hacking intent. | 100 | 76 | Use JWT (JSON Web Token - token encoded from data payload using a secret established the server) to authenticate the user and share the information with the server. Implementation of a well-designed firewall. With that purpose, it would be needed to know the representatives (end-to-end systems involved) and to create filtering rules that do not allow the traffic for any other system but the representatives. The corporative email can only be used for communications within the company. | The security team from Rainforest take the necessary measures given the circunstances. | The Rainforest's Security Department should investigate the cause of the attack andstudy measures to avoid future penetrations attempts.
| Sensor perturbation [s.4] | Decalibration, external disruption (leaves fallen over luminosity sensor, move the humidity sensor to a bottle of water, etc.). | 30 | 30 | After all the testing and demonstrations are done, before the device is commercialized, protect the sensors by a carcass. | If the device perceives what would be considered to be unexpected readings, the user should be notified to take the appropiate measures (clean the sensor, substitute it, etc.). | The user should be asked about the reason for the readings and add the cause to the database so that the system is able to predict future perturbations.
| Bluejacking attack (and similar) [s.5] | The bluetooth connection that the ESP32 counts with might cause threats to which the system might be exposed. It can be the door to possible attacks. | 80 | 4 | Deactivate the Bluetooth connection and used the Wi-Fi connection instead to interact with the web page and the Alexa service. | Not needed after deactivating the Bluetooth. | Not needed after deactivating the Bluetooth.
| Interception or extraction of data [s.6] | Through some tools, hackers can access the packages that the devices send to each other to communicate, obtaining some sensitive information. | 90 | 6 | Data encryption using AES for the ESP32 incoming/outgoing data. | Lock any communication that contains personal data (such as usernames, credentials, etc.) and use the automated services integrated in the system. The user must be notified of the security breach. The user must reset all credentials and take the steps suggested by the security team. | Unlock all the services. Notify the user about the rehabilitation of the services and that the security breach has been solved.
| Device Network Overload [s.7] | The device can suffer a DoS attack or too many requests to at the same time, which could cause an overload on the network an cease the functioning of the system. | 100 | 13 | Implementation of a well-designed firewall. With that purpose, it would be needed to know the representatives (end-to-end systems involved) and to create filtering rules that do not allow the traffic for any other system but the representatives. | Lock any type of communication and use the automated services integrated in the system. | Once the attack has ceased, the Security Department should be automatically notified so that the firewall can be updated. Further measures could be taking into consideration if necessary.
| Main Server Network Overload [s.8] | The main server, hosted by AWS might be attacked by a DoS attack or have too many requests and therefore overload the network and cease the functioning of the system. | 100 | 35 | As the service is provided by a third party, that third party should be the one taking care of the security breach. | - | Besides the measures taken by AWS, Rainforesy might suggest changing the server hosting if the problem persists.

## Risk Matrix
| Negligible [1- 20] | Minor [21-40] | Moderate [41-60] | Significant [61-80] | Severe [81-100]
Very Likely [81-100]
Likely [61-80]
Possible [41-60]
Unlikely [21-40]
Very Unlikely [1-20]