## Hoja1
Distribution Chain | Risk | Description | Impact (out of 100) | Probability (%) | Preventive Actions | Contingency Plan | Restoration After Emergency State
Production | All electronic components to produce the device are running late, have been lost or stolen | Given that the supplier has any type of complication, or the pieces have been stolen, etc. It wouldn't be possible to assemble Ec⌀. | 100 | 20 | Stock extra parts on a storehouse. Have different suppliers for every part in case one of them fails. Change the supplier if the problem persists. | Use the stockage in the stockhouse. In case there is not stock left, make a new order to the other supplier. | Stock extra parts. If the problem has happend more than 2 times, without a compelling reason, a new supplier should be found to provide the stockage.
| Broken machine in assembly line | Due to a bad maintenance or by chance, one or more machines in the assembly line are broken. Not allowing the assembly of the device. | 100 | 9 | Perform periodical maintenance on the equipment and the machinery. | If it is a fast solucion: wait until the assembly line gets repaired. If it would take too long, go manual until the assembly line gets restored. | Make an investigation on what went wrong, an find a solution: maintenance more often, longer breaks, etc.
| Maintenance in assembly line | To ensure proper operation in the assembly line, every piece of equipment and machinera goes through a periodical maintenance review. | 10 | 100 | Make the maintenance of the equipment when the production is at its lowest performance, or while the assembly line is not on production. | It the maintenance has to take place at the highest production peak, only the machinery is reviewed. In case it is the equipment the one needing the maintenance, it should be taken bit by bit. | Maintenance should be scheduled better next review to avoid affecting the production.
Development | Developers asking for sick leave. | Might occur that a developer(a) does not attend to his obligation due to sickness, personal issues or other compelling reasons. | 50 | 12 | Appropiate room temperatues, air flow, room luminosity, make good use of time so that the stressful delivery periods are shorthen, etc. | If the sick leave is for a long period of time, it might be advisable to find for a substitute. | Stand-up meeting to update the employee on the state of the project (changes during absence).
| Developer resigns | Many are the reasons that could make a developer in the project resign from his position. This would leave the team without one or more members, therefore delaying the deadline. | 60 | 10 | Give the employees the most comfortable working-ambient: breaks, commodities, etc. | After the resignation has been posted, the negotations between company and employee take place. If the employee is not interested in continuing his work at the company, or the company decides the employee is not worth retaining: a selection process may start. If it is consired necessary, the selection process may start before knowing the outcome of the resignation. | The causes for the initial resignation must be looked for.
| Web page implementation delay | During the web page design some problems occur and it is not possible to finish it in the due date. | 70 | 33 | Create a realistic development plan, taking into cosideration possible small delays due to minor problems. Weekly stand-up meetings should take place to know the current state of the project compared with the planning. | Reduce unnecessary functionalities to make it to the due date. Simplify the front-end side and leave room for improvements after due date. | Start completing the functionalities that were postponed in previous phases of the development. Correct the simplified features in the front end implementation.
| Alexa implementation delay | The implementation for the controlling and monitoring system included in Alexa cannot be completed in due time. | 65 | 40 | Create a realistic development plan, taking into cosideration possible small delays due to minor problems. Weekly stand-up meetings should take place to know the current state of the project compared with the planning. | Focus the development of the webpage so that the device can be controlled with at least one of the user interfaces. | Continue the implementation of the Alexa Skill from where it was interrupted.
| Web page and Alexa implementation delay | Both the Alexa service and the web page cannot be finished in the due date. | 95 | 14 | Create a realistic development plan, taking into cosideration possible small delays due to minor problems. Weekly stand-up meetings should take place to know the current state of the project compared with the planning. | Postpone the deadline and focus resources in the web page main functionalities and aspect. | Correct the minor problems that might have been neglected before the due date (for the web page). The Alexa Skill development may continue where it was left off.
Security | Unauthozed access to the hardware |  | 80 | 5
| Sensor perturbation | Decalibration, external disruption (leaves fallen over luminosity sensor, move the humidity sensor to a bottle of water, etc.) | 30 | 30 | After all the testing and demonstrations are done, before the device is commercialized, protect the sensors by a carcass.
| Bluejacking attack (and similar) | The bluetooth connection that the ESP32 counts with might cause threats to which the system might be exposed. It can be the door to possible attacks. | 80 | 4 | Deactivate the Bluetooth connection and used the Wi-Fi connection instead to interact with the web page and the Alexa service.
| Interception or extraction of data |  | 90 | 6
| Network overload |  | 100 | 13